## Sheet1
| NoDD Algorithm Implementation Project |  | Track 1: Oct 30 Deadline (30 days)
Task | Start Date | Days Needed | Completion | Adjusted Length
Connect to Interface | 2023-09-26 | 4 | 2023-09-29 | Not Applicable
Create Prototype | 2023-09-30 | 10 | 2023-10-09 | Not Applicable
Expand Prototype | 2023-10-10 | 14 | 2023-10-23 | Not Applicable
Testing | 2023-10-24 | 4 | 2023-10-27 | Not Applicable
Flexibility / Finishing Touches | 2023-10-28 | 3 | 2023-10-30 | Not Applicable
| NoDD Algorithm Implementation Project |  | Track 2: Dec 4 Deadline (70 days)
Task | Start Date | Days Needed | Completion | Adjusted Length
Connect to Interface | 2023-09-26 | 5 | 2023-09-30 | Not Applicable
Create Prototype | 2023-10-01 | 21 | 2023-10-21 | Not Applicable
Expand Prototype | 2023-10-22 | 30 | 2023-11-20 | Not Applicable
Testing | 2023-11-21 | 7 | 2023-11-27 | Not Applicable
Flexibility / Finishing Touches | 2023-11-28 | 7 | 2023-12-04 | Not Applicable
70
Dadlines:
Starting Date:
2023-09-24
Lab Deadlines:
2023-10-18 | Interface | 22 days
2023-11-08 | 75% | 43 days
2023-12-06 | 100% | 71 days
Class Deadlines:
2023-10-31 | Working Prototype | 35 days
2023-12-05 | Final | 70 days
WORKDAYS Version Ignore:
| NoDD Algorithm Implementation Project |  | Track 2: Dec 4 Deadline (70 days)
Task | Start Date | Days Needed | Completion | Adjusted Length
Read in Data | 2023-09-26 | 5 | 2023-10-03 | 7
Structure Data | 2023-10-04 | 21 | 2023-11-02 | 29
Implement Algorithm | 2023-11-30 | 30 | 2024-01-11 | 42
Structure Output | 2024-01-12 | 7 | 2024-01-23 | 11
Output Data | 2024-01-24 | 7 | 2024-02-02 | 9
Formulas:
Completion = WORKDAY([Start Date],[Days Needed])